## Slide 1
CASHFLOW PROJECT
Status Update | May 22, 2026

## Slide 2
EXECUTIVE SUMMARY
Cashflow Project
1
Done
7
Ready for deployment
SCI-2 · SCI-3 · SCI-4 · SCI-6 · SCI-7 · SCI-9
6
In Dev / Progress
SCI-10 · SCI-12 · SCI-17 · SCI-18 · Role · CPM-040
7
Ready / Analysis / TO-DO
SCI-5 · SCI-8 · SCI-11 · SCI-13 · SCI-14 · SCI-15
21
Total Items
21
Total Items
Overview
SCI-1 is done.
Ready for deployment: SCI-2, SCI-3, SCI-4, SCI-6, SCI-7 and SCI-9. SCI-9 is due May 26; the rest are due May 22
In Development: SCI-10 and SCI-12, both due May 23.
In Progress: SCI-17 Sycamore Cross PO, SCI-18 Procurement Forecasting Individual, Keily role assignment.
Ready / Analysis / Backlog: SCI-5 and SCI-11 ready to start; SCI-14/15 in analysis; SCI-8 and SCI-13 To Do.
Main attention: SCI-9 rule definition, traceability and RITM1185647; RITM1183406 was completed by Antonio.

## Slide 3
TESTING — DETAIL
Cashflow Project
⭐ SCI-2
-
Owner: Jenn / Bushan · Assigned: Camilo Amaury
Upload Provisional Cost — Download Template broken
Download Template button is not working in Procurement Forecasting. Ready for deployment in progress. RITM1173001.
Ready for deployment
22-May
⭐ SCI-3
-
Owner: Jenn / Bushan · Assigned: Camilo Amaury
Provisional Cost Upload — 5 fields template issue
Template issue on 5-field upload. Pending Bhushan testing and Alec Bone case review. RITM1173004.
Ready for deployment
22-May
⭐ SCI-4
P1
Owner: Jenn / Julia · Assigned: Camilo Amaury
Remaining Payments Year Adjustments
Remaining payments year adjustments. Ready for deployment in progress with Camilo assigned.
Ready for deployment
22-May
⭐ SCI-6
P1
Owner: Jenn / Julia · Assigned: Camilo Amaury
Optional WBS element in Provisional Records
Optional WBS element in Provisional Records. Ready for deployment in progress.
Ready for deployment
22-May
⭐ SCI-7
P1
Owner: Jenn / Julia · Assigned: Camilo Amaury
Optional Vendor in Provisional Record manual creation
Optional Vendor manual creation. Ready for deployment in progress. Solves REQ1171550.
Ready for deployment
22-May

## Slide 4
ACTIVE & BACKLOG — DETAIL
Cashflow Project
⭐ SCI-9
P1
Owner: Jenn / Julia · Assigned: Camilo
Automatic Reduction of Provisional Cost Records
Unit tests delivered by Antonio; Cami is reviewing/retesting. Role impact remains under validation because the proposed role also allows Payment Request Forecasting changes. RITM1183406 completed by Antonio.
Ready for deployment
26-May
SCI-10
P3
Owner: Jenn / Julia · Assigned: Evelyn Rocha
Procurement Forecasting Massive App Adjustments
In Development. Evelyn will move forward with the FS, included as part of ID#458 / SCI-12.
In Development
23-May
SCI-12
P2
Owner: Alec Bone · Assigned: Evelyn Rocha
Mass Procurement Forecasting — Eye Sore Adjustments
In Development. FS analysis completed and ready to be handed over to the technical team. Analysis advanced by Cris.
In Development
23-May
SCI-8
-
Owner: TBD · Assigned: TBD
Default PO Owner filtering and limitation of records displayed
To Do. Related to RITM1185647.
To Do
TBD
SCI-14/15
-
Owner: Alec Bone · Assigned: Evelyn Rocha
WBS_ID and PROJNR/WBS internal table checks
SCI-14 and SCI-15 are currently in analysis.
In analysis
TBD

## Slide 5
ACTIVE & BACKLOG — DETAIL
Cashflow Project
⭐ SCI-20
Owner: Jenn / Julia · Assigned: Camilo
Invalidate forecasting status
Ready for deployment
26-May
SCI-21
Owner: Jenn / Julia · Assigned: Camilo
Forecasting status revision under forecasting
To Do
TBD

## Slide 6
REPORTING — STATUS UPDATE
Cashflow Project
Speaker: Walter
REPORTING
UAT
Treasury Report — IC PO with PO Procurement & AP Invoices
The approach for displaying the down payment process in the report has been defined. The view is currently under development
REPORTING
Done
Intercompany POs — Missing Project Entity PR Assignment in PO Procurement Tracking Number
Automate the report has been completed. Additionally, a meeting with Pamela is being coordinated to help standardize the purchasing process, as the procurement area currently lacks clarity on how to regularize these cases.

## Slide 7
Cashflow Project
ISSUE TRACKER
ID / SCI | Description / RITM | Status | Type | P | Due Date | Requestor / Assigned
- / SCI-1 | Forecasting Status errors (RITM1173001 / INC1082629 / INC1083663) | Done | Break Fix | - | 30-Apr | - / Camilo Amaury
449 / SCI-2 | Upload Provisional Cost — Download Template broken (RITM1173001) | Ready for deployment | Break Fix | - | 22-May | Jenn / Bushan / Camilo Amaury
449 / SCI-3 | Provisional Cost Upload — 5 fields template issue (RITM1173004) | Ready for deployment | Enhancement | - | 22-May | Jenn / Bushan / Camilo Amaury
462 / SCI-4 | Procurement Forecasting — Remaining Payments Year Adjustments | Ready for deployment | Enhancement | 1 | 22-May | Jenn / Julia / Camilo Amaury
453 / SCI-6 | Optional WBS element in Provisional Records | Ready for deployment | Enhancement | 1 | 22-May | Jenn / Julia / Camilo Amaury
454 / SCI-7 | Optional Vendor in Provisional Record manual creation (REQ1171550) | Ready for deployment | Enhancement | 1 | 22-May | Jenn / Julia / Camilo Amaury
455 / SCI-8 | Default PO Owner filtering and limitation of records displayed (RITM1185647) | To Do | Enhancement | - | TBD | - / -
463 / SCI-9 | Automatic Reduction of Provisional Cost Records (RITM1185647) | Ready for deployment | Enhancement | 1 | 26-May | Jenn / Julia / Camilo Amaury
456 / SCI-10 | Procurement Forecasting Massive app adjustments | In Development | Enhancement | 3 | 23-May | Jenn / Julia / Evelyn Rocha
458 / SCI-12 | Mass Procurement Forecasting — Eye Sore Adjustments | In Development | Enhancement | 2 | 23-May | Alec Bone / Evelyn Rocha
- / SCI-17? | PO 4501754428 — Sycamore Cross — MILL CREEK RENEWABLES LLC | In Progress | Bug | 1 | TBD | Carlos Olivencia / Camilo Amaury

## Slide 8
Cashflow Project
ISSUE TRACKER — Backlog
ID / SCI | Description / RITM | Status | Type | P | Due Date | Requestor / Assigned
- / SCI-5 + SCI-11 | Implementation to Reports views + Attachment Report external share | Ready to start | Enhancement | 1 / - | TBD | Jenn / Julia / Evelyn Rocha + TBD
- / SCI-13 | Evaluate Job of Procurement FC | To Do | Enhancement | - | TBD | Carlos Olivencia / TBD
- / SCI-14 + SCI-15 | WBS_ID check + PROJNR/WBS consistency in internal table | In analysis | Enhancement | - | TBD | Alec Bone / Evelyn Rocha
464 / SCI-18 | Procurement Forecasting — Individual | In Progress | Bug | - | TBD | - / Camilo Amaury
- / Role | Role assignment — check with AES Security Team if OK to assign role to Keily | In Progress | Enhancement | - | TBD | - / Pablo Bianco + Camilo Amaury
318 / CPM-040 | Project creation & Massive Change | In Progress | Enhancement | 2 | TBD | - / Evelyn Rocha

## Slide 9
Thank you
Cashflow Project Team · May 22, 2026
aes

## Slide 10
Cashflow Project
NEXT STEPS & PRIORITIES
IMMEDIATE (Ready for deployment / Development)
BACKLOG / OTHER PRIORITIES
449/ SCI-2
Template button broken — Ready for deployment, 22-May
449/ SCI-3
5-field template issue — Ready for deployment, 22-May
462/ SCI-4
Remaining Payments — Ready for deployment, 22-May
453/ SCI-6
Optional WBS — Ready for deployment, 22-May
454/ SCI-7
Optional Vendor — Ready for deployment, 22-May
463/ SCI-9
Automatic Reduction — Ready for deployment, 26-May
456/458 SCI-10/12
Massive App + Eye Sore FS — In Development, 23-May
SCI-17?
Sycamore Cross PO — In Progress
455/ SCI-8
Default PO Owner filtering — To Do
SCI-14/15
Internal table checks — In analysis
464/ SCI-18
Procurement Forecasting Individual — In Progress
SCI-11
Attachment Report — Ready to start
SCI-13
Evaluate Job of Procurement FC — To Do
SCI-5
Reports views — Ready to start