## Backlog
Type | RITM / INC Related | ID | JIRA code | Task name | Status | Assigned | Requestor | Priority | Due date | Initial Date | Deplayment date | Change request | Details | Status details | Internal Status | Link Jira | Comments |  | Link INC | Check JIRA
BreakFix | RITM1173001 - INC1082629 / INC1083663 |  | SCI-01 | Forecasting Status errors - Forecast status is not updating once changes are submitted. Owners need to submit, leave the line item, go back in and then leave the line item detail to see any change in forecast status. Some are also reporting that they need to submit multiple times for the status to update. | Done | Camilo Amaury |  |  | 2026-04-30 | [6 empty] | https://aes-digital.atlassian.net/browse/SCI-1 | Done |  |  | =VLOOKUP(
BreakFix | RITM1173001 | 449 | SCI-02 | In the Procurement Foresting, the "Upload Provisional Cost" Download Template button is not working | Ready to move to RPC | Camilo Amaury | Jenn / Bushan |  | 2026-05-22 | 2026-04-09 | 2026-06-02 | CHG1026240 |  |  |  | https://aes-digital.atlassian.net/browse/SCI-2 | Ready to move to RPC
Enhacement | RITM1173004 | 449 | SCI-03 | Provisional Cost Record Upload - 5 fields template issue / Update the template | Ready to move to RPC | Camilo Amaury | Jenn / Bushan |  | 2026-05-22 | 2026-04-09 | 2026-06-02 | CHG1026240 |  |  |  | https://aes-digital.atlassian.net/browse/SCI-3 | Ready to move to RPC
Enhacement | Without RITM | 462 | SCI-04 | Procurement Forecasting - Remaining Payments Year Adjustments | Ready to move to RPC | Camilo Amaury | Jenn / Julia | 1 | 2026-05-22 | 2026-04-09 | 2026-06-02 | CHG1026240 | Functional Specification is done. Tech team request some internal test | Issue in code | Pending re transport of orders | https://aes-digital.atlassian.net/browse/SCI-4 | Ready to move to RPC | 2026-05-24
Enhacement | Without RITM |  | SCI-05 | Implementation to Reports views | To Do | Evelyn Rocha | Jenn / Julia |  | TBD |  |  |  | Initial touchpoint with Julia iniciated to review task |  |  | https://aes-digital.atlassian.net/browse/SCI-5 | To Do | #VALUE!
Enhacement | Without RITM | 453 | SCI-06 | Optional WBS element in Provisional Records | Ready to move to RPC | Camilo Amaury | Jenn / Julia | 1 | 2026-05-22 | 2026-04-09 | 2026-06-02 | CHG1026240 | Functional Specification is in progress. 23-04 | Issues found 20-04 | Functional Testing 6-May | https://aes-digital.atlassian.net/browse/SCI-6 | Ready to move to RPC | 2026-05-24
Enhacement | REQ1171550 | 454 | SCI-07 | Optional Vendor in Provisional Record manual creation (solves REQ1171550) | Ready to move to RPC | Camilo Amaury | Jenn / Julia | 1 | 2026-05-22 | 2026-04-09 | 2026-06-02 | CHG1026240 | Functional Specification is done. Moving to Tech Team |  | UAT 14-MAY | https://aes-digital.atlassian.net/browse/SCI-7 | Ready to move to RPC | 2026-05-24
Enhacement | Without RITM | 455 | SCI-08 | Default PO Owner filtering and limitation of records displayed | To Do | Evelyn Rocha |  |  | TBD | [6 empty] | https://aes-digital.atlassian.net/browse/SCI-8
Enhacement |  | 463 | SCI-09 | Automatic Reduction of Provisional Cost Records | Ready to move to RPC | Camilo Amaury | Jenn / Julia | 1 | 2026-05-23 | 2026-05-02 | 2026-06-02 | CHG1026240 | Functional Specification is in progress. 23-04 | Por comentario: evitar duplicidad entre PR costs y provisionals. | Functional Testing 6-May | https://aes-digital.atlassian.net/browse/SCI-9 | Ready to move to RPC | #REF! | https://inclusionservicesjira.atlassian.net/browse/AES0705-707
Enhacement | Without RITM | 456 | SCI-10 | Adjustments to the Procurement Forecasting Massive app (remaining payments) | In Development | Evelyn Rocha | Jenn / Julia | 3 | 2026-05-23 | 2026-05-30 |  |  | Functional Spec in Done. Next Step: development with Antonio | Filters, numbers | In Development WIP - Since 5/5 | https://aes-digital.atlassian.net/browse/SCI-10 | In Development
Enhacement | Without RITM |  | SCI-11 | Attachment Report external share | To Do | TBD | Jenn / Julia |  | TBD |  |  |  | Initial touchpoint with Julia iniciated to review task |  |  | https://aes-digital.atlassian.net/browse/SCI-11 | To Do
Enhacement | Without RITM | 458 | SCI-12 | Mass Procurement Forecasting - Eye Sore Adjustments (mail with massive change) | In Development | Evelyn Rocha | Alec Bone | 2 | 2026-05-23 | 2026-05-30 |  |  | Unique FS 456 y 458 |  | In Development WIP - Since 5/5 | https://aes-digital.atlassian.net/browse/SCI-12 | In Development
Enhacement | Without RITM |  | SCI-13 | Evaluate Job of Procurement FC | To Do | TBD | Carlos Olivencia |  | TBD | [6 empty] | https://aes-digital.atlassian.net/browse/SCI-13 | To Do
Enhacement | Without RITM |  | SCI-14 | Check WBS_ID in Procurement FC internal table | To Do | Evelyn Rocha | Alec Bone |  | TBD |  |  |  | Initial touchpoint with Alec iniciated to review task |  |  | https://aes-digital.atlassian.net/browse/SCI-14 | To Do
Enhacement | Without RITM |  | SCI-15 | Review consistency between PROJNR and WBS in internal table | To Do | Evelyn Rocha | Alec Bone |  | TBD |  |  |  | Initial touchpoint with Alec iniciated to review task |  |  | https://aes-digital.atlassian.net/browse/SCI-15 | To Do
Bug | Without RITM | 464 | SCI-18 | Procurement forecasting - Individual | In Progress | Camilo Amaury | [6 empty] | Functional Spec in Done. Next Step: development with Antonio |  |  | https://aes-digital.atlassian.net/browse/SCI-18 | In Progress
Enhacement | RITM1185647 |  | SCI-19 | Rol assigment - ask with AES Security Team if it´s ok to assign role to Caily | In Progress | Pablo Bianco/Camilo Amaury | [6 empty] | Request sent to Diego 11-May. |  |  | https://aes-digital.atlassian.net/browse/SCI-19
Bug | Without RITM | 465 | SCI-20 | Invalidate forecasting status | Ready to move to RPC | Camilo Amaury | Jenn / Julia |  | 2026-05-23 | 2026-05-02 | 2026-06-02 | CHG1026240 |  |  |  | https://aes-digital.atlassian.net/browse/SCI-20
Bug |  | 466 | SCI-21 | Forecasting status revision under forescasting | To Do | Camilo Amaury |  |  | TBD | [6 empty] | https://aes-digital.atlassian.net/browse/SCI-21
Enhacement | RITM1183406 |  | SCI-22 | RITM1183406 - Filtering of down payments in procure forescating | Ready to move to RPC | Camilo Amaury | Jenn / Julia |  | 2026-05-23 | 2026-05-02 | 2026-06-02 | CHG1026240 |  |  |  | SCI-22 - RITM1183406 - Filtering of down payments in procure forecasting
Bug | Without RITM |  | SCI-23 | PO 4501754428 - Sycamore Cross - MILL CREEK RENEWABLES LLC | In Progress | Camilo Amaury | Carlos Olivencia | 1 | TBD |  |  |  | Call with Walter report view to get details to create Fiori APP |  |  | SCI-23 - PO 4501754428 - Sycamore Cross - MILL CREEK RENEWABLES LLC | In Progress
Enhacement | Without RITM | 318 | SCI-24 | 318-[CPM-040] Project creation & Massive Change | In analysis | Evelyn Rocha |  | 1 | TBD | 2026-05-27 |  |  | FS done 12/05 Wating DEV |  | Blocked | SCI-24 - 318-[CPM-040] Project creation & Massive Change
Enhacement | Without RITM |  | SCI-25 | New logic for provisional record for PO | In analysis | Evelyn Rocha |  |  |  | 2026-05-27 | [5 empty] | SCI-25 - 467-Project Monitoring Accounting
Enhacement | Without RITM |  | SCI-26 | CPM Additional Field Needed | To Do | TBD | [9 empty] | SCI-26 - Download RPC code from Procurement Forecasting / review CPM repo
Enhacement | Without RITM |  | SCI-27 | Download RPC code from Procurement Forecasting / review CPM repo | To Do | TBD | [9 empty] | SCI-27 - Payment Request - Clearing of fields in duplication
Enhacement | Without RITM |  | SCI-28 | Payment Request - Clearing of fields in duplication | To Do | TBD | [9 empty] | SCI-28 - CPM Additional Field Needed
Enhacement | Without RITM |  | SCI-28 | SAP and SharePoint Template Upload | To Do | TBD | [9 empty] | SCI-29 - SAP and SharePoint Template Upload
Bug | Without RITM |  | SCI-30 | Always 2 decimals in the APP | To Do | TBD | Carlos Olivencia | [8 empty] | https://aes-digital.atlassian.net/browse/SCI-30
Formulas:
Initial Date = +[Due date]-21
Initial Date = +[Due date]+7

## Sheet3
RITM1175414 | TO-DO
RITM 1182172 | TO-DO
INC1113552 | TO-DO

## Sheet2
link JIRA
https://aes-digital.atlassian.net/jira/software/projects/SCI/boards/2184

## Sheet4
Issue Type | Key | Summary | Status | Due date
Story | SCI-5 | Reports views | To Do
Story | SCI-8 | Default PO Owner | To Do
Story | SCI-11 | Attachment Report external share | To Do
Story | SCI-12 | Mass Procurement Forecasting | To Do
Story | SCI-13 | Evaluate Job of Procurement FC | To Do
Story | SCI-14 | Check WBS_ID in Procurement FC internal table | To Do
Story | SCI-15 | Review consistency between PROJNR and WBS in internal table | To Do
Story | SCI-6 | Optional WBS | In Progress | 2026-04-21
Story | SCI-9 | Reduction of Provisional Cost | In Progress | 2026-04-24
Story | SCI-10 | Forecasting Massive app | In Progress
Bug | SCI-2 | Upload Provisional Cost | Testing
Bug | SCI-3 | Provisional Cost Record Upload | Testing
Story | SCI-4 | Remaining Payments Year Adjustments | Testing | 2026-04-30
Story | SCI-7 | Optional Vendor | Testing
Bug | SCI-1 | Forecasting Status errors | Done
Tipo de Incidencia | Clave | Resumen | Persona asignada | Informador | Prioridad | Estado | Resolución | Creada | Actualizada
Tarea | AES0705-696 | [SAP-CPM] Implementation to Reports views | Pablo Bianco | Maria Sanes | Medio | Tareas por hacer |  | 14/4/26 10:48 | 27/4/26 17:34
Tarea | AES0705-697 | [SAP-CPM] Optional WBS element in Provisional Records | Pablo Bianco | Maria Sanes | Medio | Tareas por hacer |  | 14/4/26 10:48 | 14/4/26 11:48
Tarea | AES0705-698 | [SAP-CPM] Optional Vendor in Provisional Record manual creation | Pablo Bianco | Maria Sanes | Medio | Tareas por hacer |  | 14/4/26 10:48 | 14/4/26 11:48
Tarea | AES0705-699 | [SAP-CPM] Default PO Owner filtering and limitation of records displayed | Pablo Bianco | Maria Sanes | Medio | Tareas por hacer |  | 14/4/26 10:48 | 14/4/26 11:48
Tarea | AES0705-700 | [SAP-CPM] Adjustments to the Procurement Forecasting Massive app | Pablo Bianco | Maria Sanes | Medio | Tareas por hacer |  | 14/4/26 10:48 | 27/4/26 17:48
Tarea | AES0705-701 | [SAP-CPM] Attachment Report external share | Pablo Bianco | Maria Sanes | Medio | Tareas por hacer |  | 14/4/26 10:48 | 14/4/26 11:48
Tarea | AES0705-702 | [SAP-CPM] Mass Procurement Forecasting - Eye Sore Adjustments | Pablo Bianco | Maria Sanes | Medio | Tareas por hacer |  | 14/4/26 10:48 | 27/4/26 18:11
Tarea | AES0705-703 | [SAP-CPM] Evaluate Job of Procurement FC | Pablo Bianco | Maria Sanes | Medio | Tareas por hacer |  | 14/4/26 10:48 | 14/4/26 11:48
Tarea | AES0705-704 | [SAP-CPM] Check WBS_ID in Procurement FC internal table | Pablo Bianco | Maria Sanes | Medio | Tareas por hacer |  | 14/4/26 10:48 | 14/4/26 11:48
Tarea | AES0705-705 | [SAP-CPM] Review consistency between PROJNR and WBS in internal table | Pablo Bianco | Maria Sanes | Medio | Tareas por hacer |  | 14/4/26 10:48 | 14/4/26 11:48
Tarea | AES0705-706 | ID#462: [SAP-CPM] Procurement Forecasting - Remaining Payments Year Adjustments | Pablo Bianco | Maria Sanes | Medio | Tareas por hacer |  | 15/4/26 10:12 | 27/4/26 16:55
Tarea | AES0705-707 | ID#463: [SAP-CPM] Automatic reduction of provisional cost records | Pablo Bianco | Maria Sanes | Medio | Tareas por hacer |  | 16/4/26 10:29 | 16/4/26 10:29
Tarea | AES0705-717 | [CPM-040] Project creation & Massive Change | Pablo Bianco | Maria Sanes | Medio | Tareas por hacer |  | 27/4/26 17:34 | 27/4/26 17:46